## SUMMARY
ELEMENTAL COST ANALYSIS
Stage : | Initial Cost Plan | [6 empty] | Date: 27th May, 2022
SUMMARY
Project: | THE LINK BUILDING, ST BARTHOLEMEW'S CHURCH
Area within external walls: |  |  |  | Gross Internal Area | 409 | m2 | 4402.476 | sq.ft.
| Element |  |  |  | Cost £ |  | £/m2 GIA | £/sq.ft. NIA
1 | substructure |  |  |  | 7000 |  | 17.1149 | 1.59
2 | structural frame |  |  |  | 33000 |  | 80.6846 | 7.4958
3 | upper floors |  |  |  | 25000 |  | 61.1247 | 5.6786
4 | roof and rainwater goods |  |  |  | 136000 |  | 332.5183 | 30.8917
5 | staircases |  |  |  | 22000 |  | 53.7897 | 4.9972
6 | external walls |  |  |  | 24000 |  | 58.6797 | 5.4515
7 | windows & external doors |  |  |  | 65000 |  | 158.9242 | 14.7644
8 | internal walls |  |  |  | 41000 |  | 100.2445 | 9.3129
9 | internal doors and ironmongery |  |  |  | 32000 |  | 78.2396 | 7.2686
10 | wall finishes |  |  |  | 9000 |  | 22.0049 | 2.0443
11 | floor finishes |  |  |  | 50000 |  | 122.2494 | 11.3572
12 | ceiling finishes |  |  |  | 39000 |  | 95.3545 | 8.8587
13 | decorations |  |  |  | 26000 |  | 63.5697 | 5.9058
14 | fittings |  |  |  | 66000 |  | 161.3692 | 14.9916
15 | sanitary fittings and wastes |  |  |  | 22000 |  | 53.7897 | 4.9972
16 | mechanical services installations |  |  |  | 93000 |  | 227.3839 | 21.1245
17 | electrical services installations |  |  |  | 99000 |  | 242.0538 | 22.4873
18 | Lifts |  |  |  | 62000 |  | 151.5892 | 14.083
19 | builders work on services |  |  |  | 16000 |  | 39.1198 | 3.6343
|  |  |  | Building Sub-Total | 867000 |  | 2119.8044 | 196.9346
20 | repairs |  |  |  | 12000 |  | 29.3399 | 2.7257
21 | demolitions and alterations |  |  |  | 48000 |  | 117.3594 | 10.903
22 | external works |  |  |  | 70000 |  | 171.1491 | 15.9001
23 | incoming services |  |  |  | 5000 |  | 12.2249 | 1.1357
24 | Scaffold Access and Temp Roof |  |  |  | 54000 |  | 132.0293 | 12.2658
|  |  |  | Sub-Total | 1056000 |  | 2581.9071 | 239.865
25 | preliminaries | 11% |  |  | 116160 |  | 284.0098 | 26.3852
26 | overheads & profit | 7.5% | part incl rates |  | 87912 |  | 214.9438 | 19.9688
27 | design & price risk | 7.5% |  |  | 94505.4 |  | 231.0645 | 21.4664
|  |  |  | TOTAL CURRENT DAY COST £ | 1354577.4 |  | 3311.9252 | 307.6854
Other Costs
28 | Inflation for a summer 2024 start based
on BCIS tender indices (May 2022 to
| spring 2024) |  |  |  | 94820.418 |  | 231.8348 | 21.538
|  |  |  | TOTAL COST £ | 1449397.818 |  | 3543.7599 | 329.2233
| add 7.2% increase re 2025 start |  |  |  | 104356.6429
|  | Total Cost |  |  | 1553754.4609
Exclusions : -
| a) Value Added Tax |  |  |  | 310750.8922
b) Professional Fees
c) Loose fittings and fixtures
d) Soft Landscaping
e) Local Authorities' charges
f) Decanting Costs
g) Asbestos survey and removal
h) Additional surveys
i) Furniture and fittings
j) Curtains and blinds
k) Telephone and satellite TV installations
l) Additional insurances

## Dems and Alts
| Quant | Unit | Rate | Total
Demolitions and Alterations to existing structures
Removal of structures
Break out and remove existing brick retaining walls and railing etc. and dispose | 1 | Nr | 1500 | 1500
Remove central supporting column including providing temporary propping as necessary (Provisional) | 1 | Nr | 5000 | 5000
Remove of existing 1st floor joists etc. and dispose | 253.47 | m2 | 45 | 11406.15
Removal of fittings and fixtures
Remove existing joinery (wardrobe unit) about 3200 mm long and dispose | 1 | Nr | 300 | 300
Remove existing Kitchen and dispose | 1 | Nr | 600 | 600
Ditto but cupboards in room adjacent | 1 | Nr | 200 | 200
Remove all sanitaryware etc. in toilet areas and dispose say | 1 | Nr | 1500 | 1500
Removing folding partitions and dispose about 4500 mm long incl making good | 3 | Nr | 200 | 600
Remove all internal doors (not already incl in partition removals quants below) and dispose | 7 | Nr | 65 | 455
Removal of finishes
Remove existing floor coverings and dispose | 253.47 | m2 | 7.5 | 1901.025
Remove existing ceilings and dispose | 253.47 | m2 | 15 | 3802.05
Remove existing skirtings and dispose | 102.1 | m | 5 | 510.5
Removing external walls and internal partitions etc.
Cut away and remove 400 mm thick external wall about 2700 x 3000 mm and dispose surplus materials off site | 1 | nr | 1620 | 1620
Extra for making good surroundinf finishes | 1 | nr | 500 | 500
Take down and remove internal partitions and dispose off site | 85.88 | m2 | 50 | 4294
Take down and remove 400 mm thick masonry wall adjacent to WC's and dispose | 8.25 | m2 | 200 | 1650
Extra for installing steel beam if structural (Provisional) | 0.21375 | T | 5750 | 1229.0625
Extra for padstones | 2 | nr | 200 | 400
Take down and remove 400 mm thick masonry wall adjacent to WC's and dispose | 8.25 | m2 | 200 | 1650
Extra for installing steel beam if structural (Provisional) | 0.1125 | T | 5750 | 646.875
Extra for padstones | 2 | nr | 200 | 400
Forming and Infilling openings etc.
Forming opening in 400 mm thick masonry wall for new kitchen hatch size about 1000 x 1000 mm | 1 | nr | 800 | 800
Forming opening in 400 mm thick wall for new door size abut 800 x 2000 mm | 1 | nr | 1000 | 1000
Forming opening in 275 mm thick wall for new door size abut 800 x 2000 mm | 1 | nr | 850 | 850
Forming opening in 400 mm thick wall on 1st floor between storage and room 5 | 1 | nr | 1000 | 1000
Filling in opening about 1000 x 2000 mm in cavity blockwork plastered both sides | 1 | nr | 1250 | 1250
Filling in opening about 900 x 2000 mm in timber studwork and plasterboard and skim etc. | 1 | nr | 750 | 750
Adapt, cut away and enlarge opening as necessary to allow for 1000 mm wide door in WC adjacent | 1 | nr | 800 | 800
Works assocaited with blocking up/fixing shut existing kithcen entrance door | 1 | nr | 1000 | 1000
Generally
Sundry removal of minor fixings, window blinds/curtains and the like say 4 labourer man days | 4 | days | 200 | 800
Total to Summary |  |  |  | 48414.6625

## Repairs
| Quant | Unit | Rate | Total
Repairs
Repairs/repointing to external elevations | 1 | No | 5000 | 5000
Plaster Repairs generally (Provisional) | 1 | No | 5000 | 5000
Sundry repairs | 1 | No | 1500 | 1500
Total to Summary |  |  |  | 11500

## substructure
| Quant | Unit | Rate | Total
Substructure
New Entrance Porch
Excavate for and including concrete strip foundations | 2.565 | m3 | 300 | 769.5
Excavate for new extension floor build up and dispose | 3.375 | m3 | 60 | 202.5
Earthwork support | 4.5 | m2 | 30 | 135
Cast new 200 mm concrete slab | 1.8 | m3 | 300 | 540
Extra for steel reinforcement bars | 0.27 | T | 2000 | 540
Extra for formwork | 12 | m | 30 | 360
Extra for compacting base of excavation | 9 | m2 | 2 | 18
Extra for 150 mm type 1 sub-base | 9 | m2 | 20 | 180
Extra for 50 mm blinding | 9 | m2 | 12.5 | 112.5
Extra for DPM | 9 | m2 | 4.5 | 40.5
Extra for 100 mm insulation | 9 | m2 | 30 | 270
Extra for 75 mm screed | 9 | m2 | 40 | 360
Extra for connections with existing slab incl movement joints | 6 | m | 75 | 450
Link Building
Excavate for and including concrete pad foundations for link building posts | 8 | Nr | 325 | 2600
Total to Summary |  |  |  | 6578

## frame
| Quant | Unit | Rate | Total
Frame
Steelwork spanning room 1 (no details so have made assumptions on what may be required) (PROVISIONAL) | 3.78 | T | 5750 | 21735
Extra for timbers bolted into web of steel beam ready to receive joists and hangers | 66 | m | 25 | 1650
Padstones built into existing masonry ready to receive steels | 8 | nr | 250 | 2000
New timber frame and posts etc. for link between church and Link building (no details) | 1 | nr | 5000 | 5000
Sundry structural works say | 1 | nr | 2500 | 2500
Total to Summary |  |  |  | 32885

## upper floors
| Quant | Unit | Rate | Total
Upper floors
Provide new timber floor construction comprising 50 x 200 mm joists and joist hangers, wall plates etc. | 253.47 | m2 | 100 | 25347
Total to Summary |  |  |  | 25347

## roof
| Quant | Unit | Rate | Total
Roofs
Replace Main roof
Take up existing tiles, battens and felt etc. and dispose off site | 406 | m2 | 20 | 8120
Tiled roof coverings on and including battens and felt | 406 | m2 | 145 | 58870
Extra for ridge | 58.9 | m | 35 | 2061.5
Extra for double course at eaves | 64.65 | m | 20 | 1293
Extra for valley | 41.25 | m | 30 | 1237.5
Extra for verge | 70.846 | m | 30 | 2125.38
Extra for hip | 6 | m | 35 | 210
Remove rainwater gutters, dispose and renew in cast iron | 53.45 | m | 7.5 | 400.875
Extra for providing new in cast iron | 64.65 | m | 60 | 3879
Remove rainwater pipes, dispose and renew in cast iron | 32 | m | 7.5 | 240
Extra for providing new in cast iron | 32 | m | 55 | 1760
Extra for shoe | 11 | nr | 100 | 1100
Remove existing lead flashings say | 31.2 | m | 7.5 | 234
Provide new lead flashings etc. | 72.3 | m | 75 | 5422.5
Insulate between rafters (area not covered by insulation in ceilings finishes tab) | 180 | m2 | 35 | 6300
Velux rooflights including trimming out as necessary | 5 | Nr | 1250 | 6250
New Link Roof
New timber roof construction to form link | 50.24 | m2 | 85 | 4270.4
Tiled roof coverings on and including battens and felt | 50.24 | m2 | 145 | 7284.8
Extra for ridge | 9 | m | 35 | 315
Extra for double course at eaves | 18 | m | 20 | 360
Ceiling to underside of link (details unknown) say | 23.04 | m2 | 130 | 2995.2
New gutters in cast iron | 18 | m | 67.5 | 1215
New rainwater pipes in cast iron | 5 | m | 62.5 | 312.5
Extra for shoe | 2 | nr | 100 | 200
Provide new lead flashings etc. | 4 | m | 75 | 300
New Dormer Roofs
New timber roof construction to form new roof extension and dormer | 40.9571 | m2 | 105 | 4300.4955
Extra for junctions with existing roof on dormers | 2 | nr | 500 | 1000
Extra for junctions with existing roof on new extension roof | 1 | nr | 1000 | 1000
Tiled roof coverings on and including battens and felt |  | m2 | 145 | Incl abv
New gutters in cast iron |  | m | 67.5 | Incl abv
Provide new lead flashings etc. |  | m | 75 | Incl abv
New Flat Roof Extension
Flat roofs incl joists, ply, insulation and single ply coverings | 18.14 | m2 | 285 | 5169.9
Extra for dealing with rainwater | 1 | No | 750 | 750
Extra for upstands etc. | 17 | m | 50 | 850
New Porch Roof
Flat roofs incl joists, ply, insulation and lead | 6.3 | m2 | 520 | 3276
Extra for dealing with rainwater | 1 | No | 500 | 500
Extra for upstands etc. | 5.05 | m | 90 | 454.5
NE Flat Roof
Renewing flat roof at NE corner in lead | 4.97 | m2 | 385 | 1913.45
Extra for upstands etc. | 4.5 | m | 90 | 405
Total to Summary |  |  |  | 136376.0005

## staircases
| Quant | Unit | Rate | Total
Staircases
New Staircase around lift | 1 | Nr | 20000 | 20000
Forming steps in Room 6 | 1 | Nr | 1500 | 1500
Total to Summary |  |  |  | 21500

## ext walls
| Quant | Unit | Rate | Total
External walls
Construct new plinth to entrance porch comprising cavity constrcution with outer skin of stonework, cavity, insulation, inner skin of blockwork and plastered internally | 2.8 | m2 | 500 | 1400
Extra for bonding into existing masonry | 1 | nr | 300 | 300
Extra for coping stone to top of plinth | 3.5 | m | 250 | 875
Curtain wall glazing to entrance extension above plinth | 6.307 | m2 | 1000 | 6307
Externals walls at entrance from new link (assume cavity wall incl rendered blockwork) | 9 | m2 | 235 | 2115
Extra for bonding into existing masonry | 9.7 | m | 50 | 485
External walls where new flat roof formed (details not clear from dwgs) - PROVISIONAL | 1 | nr | 5000 | 5000
Sundry works to external walls north of Room 6 (details unknown but the drawings appears to indicate new walls here?) (PROVISIONAL) - TBC | 1 | nr | 7500 | 7500
Total to Summary |  |  |  | 23982

## wdws & extl drs
| Quant | Unit | Rate | Total
Windows & external doors
Windows
Remove existing windows and dispose off site | 17 | Nr | 100 | 1700
Extra for removing all metal security bars and grilles etc. And make good stonework Say | 17 | Nr | 150 | 2550
New double glazed powder coated aluminium windows : -
North West Elevation
Incl curved head | 4.46 | m2 | 1250 | 5575
Dormer windows | 3.0784 | m2 | 1000 | 3078.384
Square/Rectangular | 3.5705 | m2 | 900 | 3213.45
Arrow slit window | 1 | nr | 350 | 350
South West Elevation
Incl curved head | 6.64 | m2 | 1250 | 8300
Square/Rectangular | 4.92 | m2 | 900 | 4428
Arrow slit window | 1 | nr | 350 | 350
Small window with curved head | 3 | nr | 500 | 1500
South East Elevation
Incl curved head | 3.43 | m2 | 1250 | 4287.5
Square/Rectangular | 0.67 | m2 | 900 | 603
Small window with curved head | 1 | nr | 500 | 500
North East Elevation
Incl curved head | 2.68 | m2 | 1250 | 3350
Dormer windows | 2.87 | m2 | 1000 | 2870
Square/Rectangular | 4.16 | m2 | 900 | 3744
Provisional allowance for new security bars etc. to windows adajent to road say | 1 | No | 4000 | 4000
Works to existing windows where new 1st floor construction splits the window in 2 (no details) say | 3 | Nr | 1500 | 4500
External Doors
Remove existing and dispose | 1 | No | 75 | 75
Remove door and screen from link entrance | 1 | No | 150 | 150
Double entrance door incl. ironmongery (assume part glazed) | 1 | nr | 3300 | 3300
Double entrance doors to new link incl new frame and ironmongery and curved head (assume glazed) | 1 | nr | 5097.26 | 5097.26
Single door, frame and ironmongery to Kitchen | 1 | nr | 1150 | 1150
Total to Summary |  |  |  | 64671.594

## int walls
| Quant | Unit | Rate | Total
Internal walls
Stud partition walls incl studwork, acoustic insulation and SoundBloc board and skim both sides
Ground Floor | 79.2 | m2 | 130 | 10296
Internal block masonry wall to WC about 700 mm wide x 3300 mm high plastered both sides | 1 | nr | 500 | 500
Stud partition walls incl studwork, acoustic insulation and SoundBloc board and skim one side only to perimeter of rooms
First Floor | 101.25 | m2 | 115 | 11643.75
Stud partition walls incl studwork, acoustic insulation and SoundBloc board and skim both sides
First Floor | 55.9 | m2 | 130 | 7267
Line existing walls to new entrance (formally external walls) with plasterboard and skim on and incl battens | 9.9 | m2 | 75 | 742.5
Extra for work at junctions with existing | 12.6 | m | 35 | 441
Soundproof office pod in Room 2 on GF (Provisional) say | 1 | nr | 10000 | 10000
Total to Summary |  |  |  | 40890.25

## Int doors
| Quant | Unit | Rate | Total
Internal doors
Single doors incl. frames + ironmongery | 18 | nr | 1150 | 20700
Double timber/glazed doors incl. frames + ironmongery (from lift lobby into room 1) | 1 | nr | 2000 | 2000
Double fully glazed doors and side lights incl. ironmongery from lobby into room 1 | 1 | nr | 6562.5 | 6562.5
Boiler Room door say | 1 | nr | 750 | 750
Allow for access Panels | 6 | nr | 250 | 1500
Total to Summary |  |  |  | 31512.5

## wall finishes
| Quant | Unit | Rate | Total
Wall finishes
Tiling to WC's and bathrooms etc. - full height to 2 of 4 walls PC £35/m2 supply
WC | 21.45 | m2 | 95 | 2037.75
Toilets | 32.01 | m2 | 95 | 3040.95
WC (next Room 2) | 13.86 | m2 | 95 | 1316.7
WC (FF) | 6.15 | m2 | 95 | 584.25
Disabled WC (FF) | 10.65 | m2 | 95 | 1011.75
Tiled splashback to kitchen say | 12.5 | m | 50 | 625
Extra over for kerdiboard in shower area ready to receive tiling (msd separately) | 7.9 | m2 | 45 | 355.5
Total to Summary |  |  |  | 8971.9

## floor finishes
| Quant | Unit | Rate | Total
Floor finishes
Engineered flooring (say £60/m2 supply)
Lift Lobby and stair area | 35.09 | m2 | 110 | 3859.9
Main Space (Room 1) | 106.19 | m2 | 110 | 11680.9
Office (Room 2) | 22.97 | m2 | 110 | 2526.7
Vinyl
Boiler Room | 2.8 | m2 | 55 | 154
Storage adjacent to lift | 7.07 | m2 | 55 | 388.85
Storage (adjacent WC) | 8.98 | m2 | 55 | 493.9
Ceramic Tiling (say £35/m2 supply)
Kitchen | 26.83 | m2 | 90 | 2414.7
WC | 8.08 | m2 | 90 | 727.2
Toilets | 14.42 | m2 | 90 | 1297.8
WC (next Room 2) | 4.06 | m2 | 90 | 365.4
Entrance Lobby | 16.98 | m2 | 90 | 1528.2
WC | 1.73 | m2 | 90 | 155.7
Disabled WC | 4.21 | m2 | 90 | 378.9
Carpet (First Floor)
Room 6 | 21.29 | m2 | 60 | 1277.4
Room 3 | 58.69 | m2 | 60 | 3521.4
Lift Lobby and stair | 25.29 | m2 | 60 | 1517.4
Room 4 | 10.66 | m2 | 60 | 639.6
Room 5 | 12.81 | m2 | 60 | 768.6
Storage | 20.44 | m2 | 60 | 1226.4
18 mm ply to all FF areas | 155.12 | m2 | 40 | 6204.8
Latex levelling screed to all GF areas | 253.47 | m2 | 17.5 | 4435.725
New timber skirtings as required
Grd Floor | 120.6 | m | 22.5 | 2713.5
1st Floor | 93.25 | m | 22.5 | 2098.125
Total to Summary |  |  |  | 50375.1

## ceiling finishes
| Quant | Unit | Rate | Total
Ceiling finishes
New ceiling to underside of joists on GF (assume acoustic ceiling comprising 2 layers SoundBloc board, resilient bars and skim finish) | 253.47 | m2 | 70 | 17742.9
New standard plasterboard and skim ceiling to underside of rafters on FF | 225.9 | m2 | 35 | 7906.5
Extra for insualtion between rafters (assume Kingspan) | 225.9 | m2 | 40 | 9036
Standard covings on GF (no details) say | 173.6 | m | 25 | 4340
Total to Summary |  |  |  | 39025.4

## Decorations
| Quant | Unit | Rate | Total
Decorations
General internal Decorations | 409 | m2 | 55 | 22495
External Redecorations : -
Existing Fascias and soffits etc. | 64.95 | m | 22.5 | 1461.375
Existing bargeboards | 70.846 | m | 22.5 | 1594.035
Total to Summary |  |  |  | 25550.41

## fittings
| Quant | Unit | Rate | Total
Fittings
Kitchen and appliances (Provisional Allowance) | 1 | item | 35000 | 35000
Kitchen Hatch | 1 | item | 750 | 750
Joinery generally : -
Toilets (GF) | 1.5 | m | 1500 | 2250
Room 2 (GF) | 2.6 | m | 1500 | 3900
Room 3 (FF) | 2 | m | 1500 | 3000
Room 5 (FF) | 3.85 | m | 1500 | 5775
Room 6 (FF) | 3.5 | m | 1500 | 5250
Storage Room (GF) | 1 | Nr | 3000 | 3000
Storage Room (FF) | 1 | Nr | 5000 | 5000
Tea Point | 2 | Nr | 1000 | 2000
Total to Summary |  |  |  | 65925

## sanitary
| Quant | Unit | Rate | Total
Sanitary fittings
GF Accessible WC (adjacent to Room 2) | 1 | nr | 2500 | 2500
GF Accessible WC and Shower Room (adjacent to Kitchen) | 1 | nr | 5500 | 5500
GF Toilets and Accessible WC (adjacent to Lift Lobby) | 1 | nr | 6300 | 6300
FF Accessible WC (adjacent to Lift Lobby) | 1 | nr | 2500 | 2500
FF WC (adjacent to Lift Lobby) | 1 | nr | 2000 | 2000
Mirrors and sundries etc. Say | 5 | nr | 500 | 2500
Waterproofing in Shower Room say | 1 | nr | 750 | 750
Total to Summary |  |  |  | 22050

## mech
| Quant | Unit | Rate | Total
Mechanical installation
Preliminaries | 409 | m2 | 5 | 2045
Stripping out existing installations | 254 | m2 | 7.5 | 1905
Gas fired boiler | 1 | No | 5500 | 5500
Extra over for ASHP | 1 | No | 5500 | 5500
Extra for ASHP housing | 1 | No | 2000 | 2000
Heating via radiators | 409 | m2 | 115 | 47035
Controls (basic) | 1 | No | 2000 | 2000
Above ground drainage | 1 | No | 3000 | 3000
Below ground drainage | 1 | No | 3000 | 3000
H & C Water | 409 | m2 | 40 | 16360
Ventilation | 1 | No | 2400 | 2400
Sundries/commissioning | 1 | No | 2500 | 2500
Total to Summary |  |  |  | 93245

## elec
| Quant | Unit | Rate | Total
Electrical installation
Preliminaries | 409 | m2 | 5 | 2045
Stripping out existing installations | 254 | m2 | 7.5 | 1905
Mains Distribution | 1 | Nr | 3500 | 3500
Small power | 409 | m2 | 45 | 18405
New lighting | 409 | m2 | 45 | 18405
Controls (basic) | 1 | Nr | 2000 | 2000
Provisional Sum for feature lighting | 1 | Nr | 2000 | 2000
External lighting (Provisional) | 1 | Nr | 5000 | 5000
Fire and Security alarm | 409 | m2 | 10 | 4090
IT/Data/coms | 409 | m2 | 10 | 4090
Access Controls all as Guardian Security SW Ltd. quote dated 12.4.22 | 1 | Nr | 5339.35 | 5339.35
Solar PV Installation | 1 | Nr | 15000 | 15000
AV Installation (assume less extensive than was required in church) (Provisional) | 1 | Nr | 15000 | 15000
Sundries/commissioning | 1 | Nr | 2000 | 2000
Total to Summary |  |  |  | 98779.35

## Lifts
| Quant | Unit | Rate | Total
Lifts
Main lift | 1 | Nr | 37500 | 37500
Extra for lift pit | 1 | Nr | 3000 | 3000
External platform lift | 1 | Nr | 15000 | 15000
Extra for lift pit | 1 | Nr | 3000 | 3000
Power supplies to lift | 1 | Nr | 3000 | 3000
Total to Summary |  |  |  | 61500

## bwic
|  | Quant | Unit | Rate | Total
Builders work in connection
17.1.01 | BWIC Mech, Elec and Lifts | 6.5% | of | 253524.35 | 16479.0828
| Total to Summary |  |  |  | 16479.0828

## Incoming Services
| Quant | Unit | Rate | Total
Incoming Services
Upgrading incoming services | 1 | No | 5000 | 5000
1 Total to Summary |  |  |  | 5000

## Ext Wks
| Quant | Unit | Rate | Total
External works
Tarmac areas
Break up and remove existing tarmac layer and dispose off site | 218.36 | m2 | 17.5 | 3821.3
Excavate to reduce levels for new tarmac build up about 250 mm and dispose off site | 54.59 | m2 | 50 | 2729.5
Type 1 sub-base ready to receive tarmac finish (msd separately) | 218.36 | m2 | 20 | 4367.2
Geotextile membrane | 218.36 | m2 | 5 | 1091.8
Provide and lay tarmac surface | 218.36 | m2 | 85 | 18560.6
De-lineation of car parking spaces say | 4 | No | 75 | 300
Surface water drainage to tarmac areas say | 218.36 | m2 | 15 | 3275.4
Remove gate to car park, dispose and make good | 1 | No | 150 | 150
Excavate as necessary to lower external entrance lobby area and dispose off site | 26.25 | m3 | 60 | 1575
Lower ragstone entrance walls to car park by say 500 mm for full length and make good head of wall with coping (details unknown) | 18 | m | 325 | 5850
Widen existing vehicular access and make good adjacent finishes (Provisional) say | 1 | Nr | 1500 | 1500
Convert old WC block into dry store (details unknown) (Provisional Sum) | 1 | Nr | 4000 | 4000
Generally remove vegetation etc. to hard landscaped areas around Link Building and leave tidy | 1 | Nr | 500 | 500
Bicycle parking storage points say | 1 | Nr | 1000 | 1000
New Entrance Lobby Steps and paving
New concrete foundation to steps incl formwork | 1 | Nr | 3000 | 3000
New curved stone steps | 15.391 | m | 750 | 11543.25
New Stone paving at bottom of steps bedded on and including lime mortar | 8.91 | m2 | 325 | 2895.75
ACO drain at door threshold | 3.5 | m | 200 | 700
New railing say | 2.9 | m | 500 | 1450
Sundry works say | 1 | No | 1500 | 1500
Total to Summary |  |  |  | 69809.8

## Access
| Quant | Unit | Rate | Total
Scaffold
External scaffold Access | 752 | m2 | 30 | 22560
Extra for temporary roof (Provisional) | 416.5 | m2 | 65 | 27072.5
Sundries say | 1 | No | 1500 | 1500
Internal Access | 1 | No | 2500 | 2500
Total to Summary |  |  |  | 53632.5